## Taul1
Work tracking sheet |  |  |  | Name: | TRAN LE NGOC THAO
t7trle00@students.oamk.fi
Signature:
Date | Time IN | Time OUT | Time today | Sum. Time | Activities
2017-11-28 | 11:00 | 16:00 | 5h | 5h | study the project requirement
2017-11-29 | 9:00 | 12:00 | 3h | 8h | design wireframe of main page
2017-11-29 | 13:00 | 17:00 | 4h | 12h | design wireframe of number conversion page and combinatorics
2017-11-29 | 22:00 | 24:00 | 2h | 14h | design wireframe number ouput page
2017-11-30 | 21:30 | 0:00 | 2,5h | 16,5h | create combinatorics html page
2017-12-01 | 0:00 | 1:00 | 1h | 17,5h | create number system ouput html page
2017-12-01 | 11:00 | 12:00 | 1h | 18,5h | continue with number system output html page
2017-12-02 | 15:00 | 17:00 | 2h | 20,5h | design main html page
2017-12-02 | 21:00 | 24:00 | 3h | 23,5h | add javascript to number output page
2017-12-03 | 14:00 | 16:45 | 2,75h | 26,25h | modify design the whole page and finish number output page, correct wireframe for number output page
2017-12-05 | 16:00 | 17:45 | 0,75h | 27h | add javascript to combinatorics page
2017-12-05 | 23:00 | 24:00 | 1h | 28h | finish combinatorics page
2017-12-06 | 0:00 | 1:00 | 1h | 29h | design number conversion html page
2017-12-07 | 15:00 | 17:30 | 2,5h | 31,5h | add javascript to number conversion page
2017-12-07 | 20:30 | 21:00 | 0,5h | 32h | modify wireframe of number conversion page
2017-12-08 | 7:30 | 9:30 | 3h | 36h | continue designing main html page
2017-12-08 | 14:30 | 16:30 | 2h | 38h | design wireframe of random number page
2017-12-08 | 18:00 | 20:00 | 2h | 40h | create random value html page
2017-12-09 | 18:00 | 24:00 | 6h | 46h | add javascript to random values page
2017-12-10 | 16:00 | 19:00 | 3h | 49h | design wireframe of truth table page
2017-12-10 | 22:00 | 24:00 | 2h | 51h | create truth table html page
2017-12-11 | 15:00 | 20:00 | 5h | 56h | continue with designing and adding javascript to truth table page
2017-12-11 | 22:00 | 24:00 | 2h | 58h | correct small mistake and modify some design of the whole page
2017-12-12 | 21:00 | 0:00 | 3h | 61h | writing report
2017-12-13 | 7:00 | 10:00 | 3h | 64h | continue report
2017-12-13 | 15:00 | 19:00 | 4h | 68h | finish report and recheck
Total time |  |  |  | 68h